## SchoolHub_GanttPRO_NoParallel_W
Create professional Gantt charts in GanttPRO in a few clicks
SchoolHub_GanttPRO_NoParallel_WorkDays | [10 empty] | 2026-05-17 22:09
Color | WBS Number | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Budget | Actual cost | Created | Creator | Type | Project | Level
| 1 | Phase 1 – Planification & Design |  | 2026-02-09 09:22 | 2026-04-09 09:22 |  | 0 | 344 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 2 | Analyse des besoins |  | 2026-02-09 09:22 | 2026-02-17 09:22 |  | 0 | 48 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 3 | Interviews des utilisateurs cibles |  | 2026-02-09 09:22 | 2026-02-10 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 4 | Rédaction du cahier des charges |  | 2026-02-10 09:22 | 2026-02-12 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 5 | Validation des exigences fonctionnelles |  | 2026-02-12 09:22 | 2026-02-12 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 6 | Définition des user stories |  | 2026-02-13 09:22 | 2026-02-17 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 7 | Architecture système |  | 2026-02-17 09:22 | 2026-03-03 09:22 |  | 0 | 80 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 8 | Choix du pattern architectural |  | 2026-02-17 09:22 | 2026-02-20 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 9 | Définition des couches applicatives |  | 2026-02-20 09:22 | 2026-02-25 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 10 | Schéma d'architecture globale |  | 2026-02-25 09:22 | 2026-02-27 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 11 | Choix des technologies |  | 2026-02-27 09:22 | 2026-03-03 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 12 | Design base de données |  | 2026-03-03 09:22 | 2026-03-17 09:22 |  | 0 | 80 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 13 | Identification des entités métier |  | 2026-03-03 09:22 | 2026-03-05 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 14 | Modèle Conceptuel de Données (MCD) |  | 2026-03-05 09:22 | 2026-03-10 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 15 | Modèle Logique de Données (MLD) |  | 2026-03-10 09:22 | 2026-03-13 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 16 | Définition des relations et contraintes |  | 2026-03-13 09:22 | 2026-03-17 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 17 | Maquettes UI |  | 2026-03-17 09:22 | 2026-03-31 09:22 |  | 0 | 80 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 18 | Wireframes basse fidélité |  | 2026-03-17 09:22 | 2026-03-20 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 19 | Maquettes haute fidélité (Figma) |  | 2026-03-20 09:22 | 2026-03-26 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 20 | Validation UX avec utilisateurs |  | 2026-03-26 09:22 | 2026-03-30 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 21 | Définition du design system |  | 2026-03-30 09:22 | 2026-03-31 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 22 | Planification détaillée |  | 2026-03-31 09:22 | 2026-04-08 09:22 |  | 0 | 48 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 23 | Découpage en tâches et estimation |  | 2026-03-31 09:22 | 2026-04-02 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 24 | Affectation des ressources |  | 2026-04-02 09:22 | 2026-04-06 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 25 | Définition des jalons |  | 2026-04-06 09:22 | 2026-04-07 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 26 | Rédaction du PMP |  | 2026-04-07 09:22 | 2026-04-08 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 27 | Design approuvé |  | 2026-04-08 09:22 | 2026-04-08 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 28 | Phase 2 – Backend Laravel |  | 2026-04-09 09:22 | 2026-08-12 09:22 |  | 0 | 712 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 29 | Config environnement |  | 2026-04-09 09:22 | 2026-04-17 09:22 |  | 0 | 48 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 30 | Installation Laravel 12.x |  | 2026-04-09 09:22 | 2026-04-10 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 31 | Configuration .env (DB / mail / cache) |  | 2026-04-10 09:22 | 2026-04-14 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 32 | Mise en place Git et branches |  | 2026-04-14 09:22 | 2026-04-15 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 33 | Configuration Docker / Homestead |  | 2026-04-15 09:22 | 2026-04-17 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 34 | Authentification Sanctum |  | 2026-04-17 09:22 | 2026-04-30 09:22 |  | 0 | 72 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 35 | Installation Laravel Sanctum |  | 2026-04-17 09:22 | 2026-04-20 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 36 | Endpoints register / login / logout |  | 2026-04-20 09:22 | 2026-04-23 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 37 | Gestion des tokens API |  | 2026-04-23 09:22 | 2026-04-28 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 38 | Middleware d'authentification |  | 2026-04-28 09:22 | 2026-04-30 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 39 | Modèles Eloquent |  | 2026-04-30 09:22 | 2026-05-25 09:22 |  | 0 | 136 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 40 | Modèle User / Roles |  | 2026-04-30 09:22 | 2026-05-05 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 41 | Modèle Étudiant / Professeur |  | 2026-05-05 09:22 | 2026-05-11 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 42 | Modèle Classe / Matière |  | 2026-05-11 09:22 | 2026-05-14 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 43 | Modèle Note / Présence / Paiement |  | 2026-05-14 09:22 | 2026-05-25 09:22 |  | 0 | 56 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 44 | Migrations DB |  | 2026-05-25 09:22 | 2026-06-16 09:22 |  | 0 | 128 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 45 | Migration tables utilisateurs |  | 2026-05-25 09:22 | 2026-05-28 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 46 | Migration tables académiques |  | 2026-05-28 09:22 | 2026-06-04 09:22 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 47 | Migration tables financières |  | 2026-06-04 09:22 | 2026-06-11 09:22 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 48 | Seeders et factories de test |  | 2026-06-11 09:22 | 2026-06-16 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 49 | Controllers API |  | 2026-06-16 09:22 | 2026-07-13 09:22 |  | 0 | 152 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 50 | Controller Étudiants (CRUD) |  | 2026-06-16 09:22 | 2026-06-23 09:22 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 51 | Controller Notes & Bulletins |  | 2026-06-23 09:22 | 2026-06-29 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 52 | Controller Présences |  | 2026-06-29 09:22 | 2026-07-02 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 53 | Controller Emploi du temps |  | 2026-07-02 09:22 | 2026-07-08 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 54 | Controller Paiements |  | 2026-07-08 09:22 | 2026-07-13 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 55 | Rôles et autorisations |  | 2026-07-13 09:22 | 2026-07-28 09:22 |  | 0 | 88 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 56 | Définition des rôles (Admin / Prof / Parent) |  | 2026-07-13 09:22 | 2026-07-16 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 57 | Policies par ressource |  | 2026-07-16 09:22 | 2026-07-21 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 58 | Gates et permissions |  | 2026-07-21 09:22 | 2026-07-24 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 59 | Tests des accès par rôle |  | 2026-07-24 09:22 | 2026-07-28 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 60 | Tests unitaires backend |  | 2026-07-28 09:22 | 2026-08-11 09:22 |  | 0 | 80 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 61 | Tests des modèles |  | 2026-07-28 09:22 | 2026-07-31 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 62 | Tests des endpoints API (PHPUnit) |  | 2026-07-31 09:22 | 2026-08-05 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 63 | Tests d'authentification |  | 2026-08-05 09:22 | 2026-08-07 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 64 | Tests des cas limites |  | 2026-08-07 09:22 | 2026-08-11 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 65 | API fonctionnelle |  | 2026-08-11 09:22 | 2026-08-11 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 66 | Phase 3 – Frontend Vue.js |  | 2026-08-12 09:22 | 2026-11-23 09:22 |  | 0 | 584 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 67 | Config Vue.js / Vite |  | 2026-08-12 09:00 | 2026-08-19 18:00 |  | 0 | 48 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 68 | Initialisation projet Vite + Vue 3 |  | 2026-08-12 09:22 | 2026-08-13 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 69 | Configuration Vue Router |  | 2026-08-13 09:22 | 2026-08-17 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 70 | Configuration Pinia (state management) |  | 2026-08-17 09:22 | 2026-08-18 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 71 | Configuration Axios / intercepteurs |  | 2026-08-18 09:22 | 2026-08-20 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 72 | Composants réutilisables |  | 2026-08-20 09:22 | 2026-09-11 09:22 |  | 0 | 128 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 73 | Composants UI de base (Button / Input / Modal) |  | 2026-08-20 09:22 | 2026-08-27 09:22 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 74 | Composant Table avec pagination |  | 2026-08-27 09:22 | 2026-09-02 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 75 | Composant Formulaire générique |  | 2026-09-02 09:22 | 2026-09-08 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 76 | Composant Graphiques (Chart.js) |  | 2026-09-08 09:22 | 2026-09-11 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 77 | Pages de gestion |  | 2026-09-11 09:22 | 2026-10-08 09:22 |  | 0 | 152 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 78 | Page Login / Auth |  | 2026-09-11 09:22 | 2026-09-16 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 79 | Dashboard Admin |  | 2026-09-16 09:22 | 2026-09-22 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 80 | Gestion des étudiants |  | 2026-09-22 09:22 | 2026-09-28 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 81 | Gestion des notes et bulletins |  | 2026-09-28 09:22 | 2026-10-01 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 82 | Gestion des présences |  | 2026-10-01 09:22 | 2026-10-05 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 83 | Gestion de l'emploi du temps |  | 2026-10-05 09:22 | 2026-10-08 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 84 | Intégration API |  | 2026-10-08 09:00 | 2026-10-27 18:00 |  | 0 | 112 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 85 | Services API par module |  | 2026-10-08 09:22 | 2026-10-14 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 86 | Gestion des erreurs HTTP |  | 2026-10-14 09:22 | 2026-10-19 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 87 | Gestion du token Sanctum |  | 2026-10-19 09:22 | 2026-10-22 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 88 | Synchronisation état global (Pinia) |  | 2026-10-22 09:22 | 2026-10-28 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 89 | Responsive et UX |  | 2026-10-28 09:22 | 2026-11-12 09:22 |  | 0 | 88 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 90 | Adaptation mobile / tablette |  | 2026-10-28 09:22 | 2026-11-02 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 91 | Accessibilité (ARIA / contrastes) |  | 2026-11-02 09:22 | 2026-11-05 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 92 | Animations et transitions |  | 2026-11-05 09:22 | 2026-11-10 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 93 | Optimisation chargement (lazy loading) |  | 2026-11-10 09:22 | 2026-11-12 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 94 | Tests unitaires frontend |  | 2026-11-12 09:22 | 2026-11-20 09:22 |  | 0 | 48 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 95 | Tests composants (Vitest) |  | 2026-11-12 09:22 | 2026-11-16 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 96 | Tests des stores Pinia |  | 2026-11-16 09:22 | 2026-11-18 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 97 | Tests des appels API (mock) |  | 2026-11-18 09:22 | 2026-11-19 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 98 | Tests E2E critiques |  | 2026-11-19 09:22 | 2026-11-20 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 99 | UI complète |  | 2026-11-20 09:22 | 2026-11-20 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 100 | Phase 4 – Intégration & Testing |  | 2026-11-23 09:22 | 2027-02-03 09:22 |  | 0 | 416 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 101 | Tests d'intégration |  | 2026-11-23 09:22 | 2026-12-08 09:22 |  | 0 | 88 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 102 | Scénarios de test bout-en-bout |  | 2026-11-23 09:22 | 2026-11-26 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 103 | Tests des flux utilisateurs complets |  | 2026-11-26 09:22 | 2026-12-01 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 104 | Validation des rôles en conditions réelles |  | 2026-12-01 09:22 | 2026-12-04 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 105 | Tests multi-navigateurs |  | 2026-12-04 09:22 | 2026-12-08 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 106 | Tests performance |  | 2026-12-08 09:00 | 2026-12-22 18:00 |  | 0 | 88 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 107 | Profiling des requêtes SQL (N+1) |  | 2026-12-08 09:22 | 2026-12-11 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 108 | Mise en place du cache (Redis) |  | 2026-12-11 09:22 | 2026-12-16 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 109 | Optimisation des index DB |  | 2026-12-16 09:22 | 2026-12-21 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 110 | Analyse des temps de réponse API |  | 2026-12-21 09:22 | 2026-12-23 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 111 | Tests sécurité |  | 2026-12-23 09:22 | 2027-01-07 09:22 |  | 0 | 88 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 112 | Vérification CORS et headers HTTP |  | 2026-12-23 09:22 | 2026-12-25 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 113 | Tests injection SQL / XSS |  | 2026-12-25 09:22 | 2026-12-30 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 114 | Audit des routes exposées |  | 2026-12-30 09:22 | 2027-01-04 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 115 | Vérification rate limiting |  | 2027-01-04 09:22 | 2027-01-07 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 116 | Déploiement staging |  | 2027-01-07 09:00 | 2027-01-19 18:00 |  | 0 | 72 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 117 | Configuration VPS DigitalOcean |  | 2027-01-07 09:22 | 2027-01-11 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 118 | Configuration Nginx + PHP-FPM |  | 2027-01-11 09:22 | 2027-01-14 09:22 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 119 | Déploiement CI/CD basique |  | 2027-01-14 09:22 | 2027-01-18 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 120 | Configuration SSL (Let's Encrypt) |  | 2027-01-18 09:22 | 2027-01-20 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 121 | Correction bugs |  | 2027-01-20 09:22 | 2027-02-02 09:22 |  | 0 | 72 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 122 | Triage et priorisation des bugs |  | 2027-01-20 09:22 | 2027-01-22 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 123 | Correction des bugs critiques |  | 2027-01-22 09:22 | 2027-01-28 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 124 | Régression tests post-fix |  | 2027-01-28 09:22 | 2027-02-01 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 125 | Validation finale QA |  | 2027-02-01 09:22 | 2027-02-02 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 126 | Tests validés |  | 2027-02-02 09:22 | 2027-02-02 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 127 | Phase 5 – Finalisation & Documentation |  | 2027-02-03 09:22 | 2027-03-09 09:22 |  | 0 | 192 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 128 | Documentation utilisateur |  | 2027-02-03 09:22 | 2027-02-10 09:22 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 129 | Manuel administrateur |  | 2027-02-03 09:22 | 2027-02-05 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 130 | Guide professeur |  | 2027-02-05 09:22 | 2027-02-08 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 131 | Guide parent / tuteur |  | 2027-02-08 09:22 | 2027-02-09 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 132 | FAQ et dépannage courant |  | 2027-02-09 09:22 | 2027-02-10 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 133 | Documentation technique |  | 2027-02-10 09:22 | 2027-02-18 09:22 |  | 0 | 48 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 134 | Documentation API (OpenAPI / Swagger) |  | 2027-02-10 09:22 | 2027-02-12 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 135 | Architecture et design patterns |  | 2027-02-12 09:22 | 2027-02-16 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 136 | Guide installation et déploiement |  | 2027-02-16 09:22 | 2027-02-17 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 137 | Documentation du schéma DB |  | 2027-02-17 09:22 | 2027-02-18 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 138 | Tutoriels et guides |  | 2027-02-18 09:22 | 2027-02-24 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 139 | Vidéo tutoriel d'utilisation |  | 2027-02-18 09:22 | 2027-02-22 09:22 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 140 | Slides de présentation |  | 2027-02-22 09:22 | 2027-02-23 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 141 | Guide de prise en main rapide |  | 2027-02-23 09:22 | 2027-02-24 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 142 | Préparation démo |  | 2027-02-24 09:22 | 2027-03-02 09:22 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 143 | Scénario de démo complet |  | 2027-02-24 09:22 | 2027-02-25 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 144 | Jeu de données de démonstration |  | 2027-02-25 09:22 | 2027-02-26 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 145 | Répétition et timing |  | 2027-02-26 09:22 | 2027-03-01 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 146 | Support visuel (slides PFE) |  | 2027-03-01 09:22 | 2027-03-02 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 147 | Déploiement production |  | 2027-03-02 09:00 | 2027-03-05 18:00 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 148 | Checklist pré-déploiement |  | 2027-03-02 09:22 | 2027-03-03 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 149 | Migration base de données production |  | 2027-03-03 09:22 | 2027-03-04 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 150 | Déploiement application |  | 2027-03-04 09:22 | 2027-03-04 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 151 | Monitoring post-déploiement |  | 2027-03-05 09:22 | 2027-03-08 09:22 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 152 | Rapport remis |  | 2027-03-08 09:22 | 2027-03-08 09:22 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
This document has been created with the help of https://ganttpro.com online service