## SchoolHub_GanttPRO_NoParallel_W
Create professional Gantt charts in GanttPRO in a few clicks
SchoolHub_GanttPRO_NoParallel_WorkDays | [10 empty] | 2026-05-17 22:09
Color | WBS Number | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Budget | Actual cost | Created | Creator | Type | Project | Level
| 1 | Phase 1 – Planification & Design |  | 2026-02-09 09:00 | 2026-02-27 14:00 |  | 0 | 117 | 117 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 2 | Analyse des besoins |  | 2026-02-09 09:00 | 2026-02-10 17:00 |  | 0 | 16 | 16 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 3 | Interviews des utilisateurs cibles |  | 2026-02-09 09:00 | 2026-02-09 12:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 4 | Rédaction du cahier des charges |  | 2026-02-09 12:00 | 2026-02-10 12:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 5 | Validation des exigences fonctionnelles |  | 2026-02-10 12:00 | 2026-02-10 12:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 6 | Définition des user stories |  | 2026-02-10 12:00 | 2026-02-10 17:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 7 | Architecture système |  | 2026-02-10 17:00 | 2026-02-16 11:00 |  | 0 | 26 | 26 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 8 | Choix du pattern architectural |  | 2026-02-10 17:00 | 2026-02-11 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 9 | Définition des couches applicatives |  | 2026-02-11 17:00 | 2026-02-12 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 10 | Schéma d'architecture globale |  | 2026-02-12 17:00 | 2026-02-13 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 11 | Choix des technologies |  | 2026-02-13 14:00 | 2026-02-16 11:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 12 | Design base de données |  | 2026-02-16 11:00 | 2026-02-20 11:00 |  | 0 | 32 | 32 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 13 | Identification des entités métier |  | 2026-02-16 11:00 | 2026-02-16 16:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 14 | Modèle Conceptuel de Données (MCD) |  | 2026-02-16 16:00 | 2026-02-18 11:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 15 | Modèle Logique de Données (MLD) |  | 2026-02-18 11:00 | 2026-02-19 14:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 16 | Définition des relations et contraintes |  | 2026-02-19 14:00 | 2026-02-20 11:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 17 | Maquettes UI |  | 2026-02-20 11:00 | 2026-02-25 14:00 |  | 0 | 27 | 27 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 18 | Wireframes basse fidélité |  | 2026-02-20 11:00 | 2026-02-23 11:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 19 | Maquettes haute fidélité (Figma) |  | 2026-02-23 11:00 | 2026-02-24 14:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 20 | Validation UX avec utilisateurs |  | 2026-02-24 14:00 | 2026-02-25 11:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 21 | Définition du design system |  | 2026-02-25 11:00 | 2026-02-25 14:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 22 | Planification détaillée |  | 2026-02-25 14:00 | 2026-02-27 14:00 |  | 0 | 16 | 16 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 23 | Découpage en tâches et estimation |  | 2026-02-25 14:00 | 2026-02-26 11:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 24 | Affectation des ressources |  | 2026-02-26 11:00 | 2026-02-26 16:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 25 | Définition des jalons |  | 2026-02-26 16:00 | 2026-02-27 11:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 26 | Rédaction du PMP |  | 2026-02-27 11:00 | 2026-02-27 14:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 27 | Design approuvé |  | 2026-02-27 14:00 | 2026-02-27 14:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 28 | Phase 2 – Backend Laravel |  | 2026-02-27 14:00 | 2026-04-24 17:00 |  | 0 | 323 | 323 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 29 | Config environnement |  | 2026-02-27 14:00 | 2026-03-03 14:00 |  | 0 | 16 | 16 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 30 | Installation Laravel 12.x |  | 2026-02-27 14:00 | 2026-02-27 17:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 31 | Configuration .env (DB / mail / cache) |  | 2026-02-27 17:00 | 2026-03-02 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 32 | Mise en place Git et branches |  | 2026-03-02 14:00 | 2026-03-02 17:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 33 | Configuration Docker / Homestead |  | 2026-03-02 17:00 | 2026-03-03 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 34 | Authentification Sanctum |  | 2026-03-03 14:00 | 2026-03-06 14:00 |  | 0 | 24 | 24 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 35 | Installation Laravel Sanctum |  | 2026-03-03 14:00 | 2026-03-03 17:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 36 | Endpoints register / login / logout |  | 2026-03-03 17:00 | 2026-03-04 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 37 | Gestion des tokens API |  | 2026-03-04 17:00 | 2026-03-05 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 38 | Middleware d'authentification |  | 2026-03-05 17:00 | 2026-03-06 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 39 | Modèles Eloquent |  | 2026-03-06 14:00 | 2026-03-16 13:00 |  | 0 | 47 | 47 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 40 | Modèle User / Roles |  | 2026-03-06 14:00 | 2026-03-09 14:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 41 | Modèle Étudiant / Professeur |  | 2026-03-09 14:00 | 2026-03-10 17:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 42 | Modèle Classe / Matière |  | 2026-03-10 17:00 | 2026-03-11 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 43 | Modèle Note / Présence / Paiement |  | 2026-03-11 17:00 | 2026-03-16 13:00 |  | 0 | 20 | 20 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 44 | Migrations DB |  | 2026-03-16 13:00 | 2026-03-24 11:00 |  | 0 | 46 | 46 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 45 | Migration tables utilisateurs |  | 2026-03-16 13:00 | 2026-03-17 13:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 46 | Migration tables académiques |  | 2026-03-17 13:00 | 2026-03-19 12:00 |  | 0 | 15 | 15 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 47 | Migration tables financières |  | 2026-03-19 12:00 | 2026-03-23 11:00 |  | 0 | 15 | 15 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 48 | Seeders et factories de test |  | 2026-03-23 11:00 | 2026-03-24 11:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 49 | Modification du cahier des charges (CDC) (nouveaux besoins) |  | 2026-03-24 11:00 | 2026-03-24 16:00 |  | 0 | 5 | 5 | 0 | Open | Medium | Mise à jour du CDC en milieu de stage suite à l'ajout des applications mobiles et du module de paiement. |  | 0 | 0 | 2026-05-17T22:22:38 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 50 | Mise à jour de la conception (MCD / MLD) |  | 2026-03-24 16:00 | 2026-03-25 13:00 |  | 0 | 5 | 5 | 0 | Open | Medium | Conception des entités et relations pour le module mobile parent/enseignant et facturation. |  | 0 | 0 | 2026-05-17T22:22:38 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 51 | Controllers API |  | 2026-03-25 13:00 | 2026-04-10 15:00 |  | 0 | 98 | 98 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 52 | Controller Étudiants (CRUD) |  | 2026-03-25 13:00 | 2026-03-30 12:00 |  | 0 | 23 | 23 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 53 | Controller Notes & Bulletins |  | 2026-03-30 12:00 | 2026-04-01 16:00 |  | 0 | 20 | 20 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 54 | Controller Présences |  | 2026-04-01 16:00 | 2026-04-03 15:00 |  | 0 | 15 | 15 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 55 | Controller Emploi du temps |  | 2026-04-03 15:00 | 2026-04-08 14:00 |  | 0 | 23 | 23 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 56 | Controller Paiements |  | 2026-04-08 14:00 | 2026-04-10 15:00 |  | 0 | 17 | 17 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 57 | Rôles et autorisations |  | 2026-04-10 15:00 | 2026-04-17 16:00 |  | 0 | 41 | 41 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 58 | Définition des rôles (Admin / Prof / Parent) |  | 2026-04-10 15:00 | 2026-04-14 10:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 59 | Policies par ressource |  | 2026-04-14 10:00 | 2026-04-15 13:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 60 | Gates et permissions |  | 2026-04-15 13:00 | 2026-04-16 16:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 61 | Tests des accès par rôle |  | 2026-04-16 16:00 | 2026-04-17 16:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 62 | Tests unitaires backend |  | 2026-04-17 16:00 | 2026-04-24 17:00 |  | 0 | 41 | 41 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 63 | Tests des modèles |  | 2026-04-17 16:00 | 2026-04-21 11:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 64 | Tests des endpoints API (PHPUnit) |  | 2026-04-21 11:00 | 2026-04-22 17:00 |  | 0 | 14 | 14 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 65 | Tests d'authentification |  | 2026-04-22 17:00 | 2026-04-23 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 66 | Tests des cas limites |  | 2026-04-23 17:00 | 2026-04-24 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 67 | API fonctionnelle |  | 2026-04-24 17:00 | 2026-04-24 17:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 68 | Phase 3 – Frontend Vue.js |  | 2026-04-24 17:00 | 2026-05-18 13:00 |  | 0 | 124 | 124 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 69 | Config Vue.js / Vite |  | 2026-04-24 17:00 | 2026-04-28 13:00 |  | 0 | 12 | 12 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 70 | Initialisation projet Vite + Vue 3 |  | 2026-04-24 17:00 | 2026-04-27 12:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 71 | Configuration Vue Router |  | 2026-04-27 12:00 | 2026-04-27 15:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 72 | Configuration Pinia (state management) |  | 2026-04-27 15:00 | 2026-04-28 10:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 73 | Configuration Axios / intercepteurs |  | 2026-04-28 10:00 | 2026-04-28 13:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 74 | Composants réutilisables |  | 2026-04-28 13:00 | 2026-05-01 12:00 |  | 0 | 23 | 23 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 75 | Composants UI de base (Button / Input / Modal) |  | 2026-04-28 13:00 | 2026-04-29 13:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 76 | Composant Table avec pagination |  | 2026-04-29 13:00 | 2026-04-30 10:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 77 | Composant Formulaire générique |  | 2026-04-30 10:00 | 2026-04-30 15:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 78 | Composant Graphiques (Chart.js) |  | 2026-04-30 15:00 | 2026-05-01 12:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 79 | Pages de gestion |  | 2026-05-01 12:00 | 2026-05-07 14:00 |  | 0 | 34 | 34 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 80 | Page Login / Auth |  | 2026-05-01 12:00 | 2026-05-01 17:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 81 | Dashboard Admin |  | 2026-05-01 17:00 | 2026-05-04 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 82 | Gestion des étudiants |  | 2026-05-04 17:00 | 2026-05-05 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 83 | Gestion des notes et bulletins |  | 2026-05-05 17:00 | 2026-05-06 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 84 | Gestion des présences |  | 2026-05-06 14:00 | 2026-05-06 17:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 85 | Gestion de l'emploi du temps |  | 2026-05-06 17:00 | 2026-05-07 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 86 | Intégration API |  | 2026-05-07 14:00 | 2026-05-12 13:00 |  | 0 | 23 | 23 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 87 | Services API par module |  | 2026-05-07 14:00 | 2026-05-08 14:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 88 | Gestion des erreurs HTTP |  | 2026-05-08 14:00 | 2026-05-11 11:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 89 | Gestion du token Sanctum |  | 2026-05-11 11:00 | 2026-05-11 16:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 90 | Synchronisation état global (Pinia) |  | 2026-05-11 16:00 | 2026-05-12 13:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 91 | Responsive et UX |  | 2026-05-12 13:00 | 2026-05-14 15:00 |  | 0 | 18 | 18 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 92 | Adaptation mobile / tablette |  | 2026-05-12 13:00 | 2026-05-13 10:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 93 | Accessibilité (ARIA / contrastes) |  | 2026-05-13 10:00 | 2026-05-13 15:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 94 | Animations et transitions |  | 2026-05-13 15:00 | 2026-05-14 12:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 95 | Optimisation chargement (lazy loading) |  | 2026-05-14 12:00 | 2026-05-14 15:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 96 | Tests unitaires frontend |  | 2026-05-14 15:00 | 2026-05-18 13:00 |  | 0 | 14 | 14 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 97 | Tests composants (Vitest) |  | 2026-05-14 15:00 | 2026-05-15 12:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 98 | Tests des stores Pinia |  | 2026-05-15 12:00 | 2026-05-15 15:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 99 | Tests des appels API (mock) |  | 2026-05-15 15:00 | 2026-05-18 10:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 100 | Tests E2E critiques |  | 2026-05-18 10:00 | 2026-05-18 13:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 101 | UI complète |  | 2026-05-18 13:00 | 2026-05-18 13:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 102 | Phase 4 – Intégration & Testing |  | 2026-05-18 13:00 | 2026-06-10 11:00 |  | 0 | 134 | 134 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 103 | Tests d'intégration |  | 2026-05-18 13:00 | 2026-05-22 10:00 |  | 0 | 29 | 29 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 104 | Scénarios de test bout-en-bout |  | 2026-05-18 13:00 | 2026-05-19 13:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 105 | Tests des flux utilisateurs complets |  | 2026-05-19 13:00 | 2026-05-20 13:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 106 | Validation des rôles en conditions réelles |  | 2026-05-20 13:00 | 2026-05-21 13:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 107 | Tests multi-navigateurs |  | 2026-05-21 13:00 | 2026-05-22 10:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 108 | Tests performance |  | 2026-05-22 10:00 | 2026-05-27 15:00 |  | 0 | 29 | 29 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 109 | Profiling des requêtes SQL (N+1) |  | 2026-05-22 10:00 | 2026-05-25 10:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 110 | Mise en place du cache (Redis) |  | 2026-05-25 10:00 | 2026-05-26 10:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 111 | Optimisation des index DB |  | 2026-05-26 10:00 | 2026-05-27 10:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 112 | Analyse des temps de réponse API |  | 2026-05-27 10:00 | 2026-05-27 15:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 113 | Tests sécurité |  | 2026-05-27 15:00 | 2026-06-02 12:00 |  | 0 | 29 | 29 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 114 | Vérification CORS et headers HTTP |  | 2026-05-27 15:00 | 2026-05-28 12:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 115 | Tests injection SQL / XSS |  | 2026-05-28 12:00 | 2026-05-29 12:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 116 | Audit des routes exposées |  | 2026-05-29 12:00 | 2026-06-01 12:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 117 | Vérification rate limiting |  | 2026-06-01 12:00 | 2026-06-02 12:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 118 | Déploiement staging |  | 2026-06-02 12:00 | 2026-06-05 11:00 |  | 0 | 23 | 23 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 119 | Configuration VPS DigitalOcean |  | 2026-06-02 12:00 | 2026-06-02 17:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 120 | Configuration Nginx + PHP-FPM |  | 2026-06-02 17:00 | 2026-06-03 17:00 |  | 0 | 8 | 8 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 121 | Déploiement CI/CD basique |  | 2026-06-03 17:00 | 2026-06-04 14:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 122 | Configuration SSL (Let's Encrypt) |  | 2026-06-04 14:00 | 2026-06-05 11:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 123 | Correction bugs |  | 2026-06-05 11:00 | 2026-06-10 11:00 |  | 0 | 24 | 24 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 124 | Triage et priorisation des bugs |  | 2026-06-05 11:00 | 2026-06-05 16:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 125 | Correction des bugs critiques |  | 2026-06-05 16:00 | 2026-06-09 11:00 |  | 0 | 11 | 11 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 126 | Régression tests post-fix |  | 2026-06-09 11:00 | 2026-06-09 16:00 |  | 0 | 5 | 5 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 127 | Validation finale QA |  | 2026-06-09 16:00 | 2026-06-10 11:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 128 | Tests validés |  | 2026-06-10 11:00 | 2026-06-10 11:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 129 | Phase 5 – Finalisation & Documentation |  | 2026-06-10 11:00 | 2026-07-01 17:00 |  | 0 | 126 | 126 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 130 | Déploiement production |  | 2026-06-10 11:00 | 2026-06-10 17:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 131 | Checklist pré-déploiement |  | 2026-06-10 11:00 | 2026-06-10 14:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 132 | Migration base de données production |  | 2026-06-10 14:00 | 2026-06-10 17:00 |  | 0 | 3 | 3 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 133 | Déploiement application |  | 2026-06-10 17:00 | 2026-06-10 17:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 134 | Monitoring post-déploiement |  | 2026-06-10 17:00 | 2026-06-11 15:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 135 | Documentation utilisateur |  | 2026-06-11 15:00 | 2026-06-17 13:00 |  | 0 | 30 | 30 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 136 | Manuel administrateur |  | 2026-06-11 15:00 | 2026-06-15 11:00 |  | 0 | 12 | 12 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 137 | Guide professeur |  | 2026-06-15 11:00 | 2026-06-15 17:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 138 | Guide parent / tuteur |  | 2026-06-15 17:00 | 2026-06-16 15:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 139 | FAQ et dépannage courant |  | 2026-06-16 15:00 | 2026-06-17 13:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 140 | Documentation technique |  | 2026-06-17 13:00 | 2026-06-23 17:00 |  | 0 | 36 | 36 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 141 | Documentation API (OpenAPI / Swagger) |  | 2026-06-17 13:00 | 2026-06-18 17:00 |  | 0 | 12 | 12 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 142 | Architecture et design patterns |  | 2026-06-18 17:00 | 2026-06-22 13:00 |  | 0 | 12 | 12 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 143 | Guide installation et déploiement |  | 2026-06-22 13:00 | 2026-06-23 11:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 144 | Documentation du schéma DB |  | 2026-06-23 11:00 | 2026-06-23 17:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 145 | Tutoriels et guides |  | 2026-06-23 17:00 | 2026-06-26 17:00 |  | 0 | 24 | 24 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 146 | Vidéo tutoriel d'utilisation |  | 2026-06-23 17:00 | 2026-06-25 13:00 |  | 0 | 12 | 12 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 147 | Slides de présentation |  | 2026-06-25 13:00 | 2026-06-26 11:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 148 | Guide de prise en main rapide |  | 2026-06-26 11:00 | 2026-06-26 17:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 149 | Préparation démo |  | 2026-06-26 17:00 | 2026-07-01 17:00 |  | 0 | 24 | 24 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 150 | Scénario de démo complet |  | 2026-06-26 17:00 | 2026-06-29 15:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 151 | Jeu de données de démonstration |  | 2026-06-29 15:00 | 2026-06-30 13:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 152 | Répétition et timing |  | 2026-06-30 13:00 | 2026-07-01 11:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 153 | Support visuel (slides PFE) |  | 2026-07-01 11:00 | 2026-07-01 17:00 |  | 0 | 6 | 6 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | task | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
| 154 | Rapport remis |  | 2026-07-01 17:00 | 2026-07-01 17:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2026-05-17 22:23 | Mechta Abdelmoumen | milestone | SchoolHub_GanttPRO_NoParallel_WorkDays | 1
This document has been created with the help of https://ganttpro.com online service